SEDAS — Implementation Project Plan

Unified Process Construction & Transition Phases

MIS5320 Applied IS Project — Part B  ·  Week 2 Deliverable

| Team | Ashraful Islam (240135) · Huzaifa Iqbal (240220) · Sonu (250001) · Dominic Kipchirchir (240401) |
| --- | --- |
| Governing baseline | Specification Review & MVP Refinement Memorandum (Week 1, signed) |
| Methodology | Unified Process lifecycle; Agile DevSecOps + RAD delivery practices within phases |
| Repository | github.com/ailinkon/sedas |
| Status / Date | Draft for team adoption · [insert date] |

# 1. Plan on a Page

The project delivers the SEDAS MVP defined in the signed Week 1 baseline across three construction/transition sprints, gated by Unified Process milestones and evidenced continuously through the Project Log, the GitHub repository, and the test matrix. Every activity below is traceable to a requirement ID (FR/NFR), a refinement decision (R-xx), and an assessment task.

## 1.1 Schedule mapped to UP phases and assessments

| Week | UP phase | Sprint | Key activities | Milestone / assessment evidence |
| --- | --- | --- | --- | --- |
| 1 | Elaboration | — | Kick-off; specification review; refinement register; ethics re-baseline | Spec Review Memo drafted; Log entry 1 (Log review #1; Inception & Elaboration submitted) |
| 2 | Elaboration → Construction gate | Sprint 0 | Project plan; supervisor sign-off of specification; repo restructure; CI pipeline; skeleton services running end-to-end | Signed specification (baseline frozen); this plan; walking-skeleton demo |
| 3 | Construction | Sprint 1 | Detection service: dataset, baseline model, /classify API with metrics; URL service: hash-chain registry + reputation lookup; frontend: login + submission screens; first 10+ unit tests | Log review #2 (Construction Phase submitted); model metrics recorded |
| 4 | Construction | Sprint 2 | Training module v1; dashboard v1; integration of all services; system testing round 1 | Presentation 1 (MVP, 5 min); integrated MVP tagged v0.1 |
| 5 | Transition | — | MVP stakeholder demonstration; structured feedback capture; feedback disposition table; iteration-2 backlog | Transition Phase submitted; feedback disposition in Log |
| 6 | Transition | Sprint 3 | Feedback-driven enhancements; security hardening (OWASP Top 10 self-check); advanced/integration testing; performance timing vs NFR targets | Log review #3; OWASP checklist results logged |
| 7 | Transition | Sprint 3 close | Full test matrix executed (traced to FR/NFR IDs); user documentation; report drafting; release candidate tagged v1.0 | Presentation 2 (full project) |
| 8 | Transition close | — | Final report; artefact submission; handover; viva preparation (2 mock sessions) | Project Report + User Docs + Artefact; Interactive Oral/Viva |

# 2. Team Organisation (RACI)

R = Responsible (does the work), A = Accountable (owns the outcome, one per row), C = Consulted, I = Informed. Every member additionally writes unit tests for their own modules and contributes a weekly Project Log entry. A 15-minute weekly teach-back rotates so each member can explain modules they did not build — direct preparation for the individual viva.

| Activity | Ashraful | Huzaifa | Sonu | Dominic |
| --- | --- | --- | --- | --- |
| Detection service + ML model (incl. benchmark comparison) | A/R | I | I | C |
| URL verification service (hash-chain registry) | A/R | C | I | I |
| Frontend SPA + governance dashboard | A/R | C | C | I |
| Training module — code + database schema | C | I | C | A/R |
| Awareness content: micro-lessons + quiz questions (FR-05) | C | I | A/R | C |
| Security hardening + OWASP self-check (Week 6) | C | A/R | I | R |
| Test framework + CI pipeline | C | A/R | I | R |
| User documentation | C | A/R | R | I |
| Project Log custodianship + evidence collection | C | C | A/R | C |
| Presentations coordination (Weeks 4 & 7) | C | C | A/R | C |
| Final report integration | A/R | R | C | C |
| Stakeholder liaison / sign-offs / supervisor GitHub access | A/R | I | I | I |

# 3. Technology Stack and Justification

Each selection is stated against the alternatives considered and, where relevant, against the original Part A specification with the corresponding refinement register reference.

| Layer | Chosen | Alternatives considered | Justification |
| --- | --- | --- | --- |
| Backend services | Python 3.11 + FastAPI | Flask; Node.js/Express; Django | Native fit with the ML ecosystem (scikit-learn, HuggingFace); automatic OpenAPI documentation supports the documented-API requirement (FR-09); async performance adequate for NFR-02/03; team proficiency is highest in Python. |
| ML model | TF-IDF + Logistic Regression baseline, then fine-tuned DistilBERT | Full BERT; LSTM hybrid (Part A); rule-based | Two-model strategy yields a comparison for the report and de-risks the timeline: the baseline guarantees demonstrable results in Sprint 1; DistilBERT retains the transformer approach justified in Part A at a fraction of full BERT's compute (R-05). |
| URL trust registry | Hash-chained PostgreSQL table + PhishTank/Google Safe Browsing lookup | Ethereum smart contract (Part A); plain blocklist table | Preserves tamper-evidence (each record hashes its predecessor) without gas fees, wallets or block latency (R-01); a plain table was rejected as it reintroduces the single-point-of-tampering weakness Part A §4.2 criticised. |
| Frontend | React SPA + Recharts | Vue; server-rendered templates | Matches Part A §3.2 specification; Recharts covers all dashboard visualisations (FR-07) without licence cost; SPA cleanly separates the API layer, preserving the microservice model. |
| Database | PostgreSQL (SQLite in dev) | MySQL; MongoDB | Relational integrity suits user/progress/audit data (FR-06, NFR-08); Part A data architecture is relational; SQLite keeps local development friction near zero. |
| Orchestration | Docker Compose | Kubernetes (Part A); bare processes | One-command reproducible environment for markers; retains per-service containers so the Kubernetes migration path is demonstrable (R-06). |
| Version control & CI | GitHub (existing ailinkon/sedas) + GitHub Actions running pytest on push | GitLab; no CI | Unit outline names Git/GitHub as required tooling; Actions delivers the automated-testing pipeline promised in Part A §4.1 at zero cost; commit history doubles as viva evidence. |
| Testing | pytest (unit/integration) + manual UAT scripts | unittest; Selenium end-to-end | pytest fixtures suit API testing; full browser automation adds cost disproportionate to MVP scope — UAT is scripted manually and evidenced with screenshots in the test matrix. |

# 4. Development Workflow and Version Control

- Branching. main is protected; all work happens on feature branches named feature/<module>-<short-description>, merged by pull request with at least one reviewer from another module.

- Commits. Commit messages follow the pattern <module>: <imperative summary> (e.g., detection: add TF-IDF baseline pipeline). The history is assessment evidence — it must read as a narrative of the build.

- Continuous integration. GitHub Actions runs the pytest suite on every push and pull request; a failing pipeline blocks merge. This operationalises the automated testing commitment of Part A §4.1.

- Release tagging. v0.1 at the end of Sprint 2 (integrated MVP, Week 4), v0.2 after feedback-driven iteration (Week 6), v1.0 release candidate (Week 7). Tags give the Log's version history concrete anchors.

- Hygiene. No secrets in the repository; configuration via environment variables with a committed .env.example; dependency versions pinned in requirements.txt and package-lock.json.

# 5. Quality and Testing Strategy

- Unit tests. pytest per service, written alongside features by the module owner; target coverage of core logic paths, not vanity percentages.

- Integration tests. API-level tests across service boundaries from Sprint 2 onward, run in CI.

- Model evaluation. Held-out test set; confusion matrix, precision, recall, F1, false-positive rate reported against NFR-01 with gap analysis (R-04).

- UAT. Scripted user-acceptance scenarios derived from the Part A user journeys, executed during the Week 5 stakeholder demonstration and again on v1.0; results captured in the traced test matrix (Test ID → FR/NFR ID → input → expected → actual → pass/fail).

- Security testing. Week 6 OWASP Top 10 self-assessment on the artefact itself; findings and remediations logged.

# 6. Risk Register

L = likelihood, I = impact (H/M/L). Reviewed at each weekly meeting; changes minuted in the Log.

| ID | Risk | L | I | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| RK-01 | ML model underperforms Part A KPI (F1 ≥ 0.95) | M | M | Two-model strategy; honest gap analysis pre-approved in refinement register (R-04); metrics reported transparently | Ashraful |
| RK-02 | Team member unavailable during a sprint | M | H | Weekly teach-backs so every module has a second knowledgeable member; tasks tracked on shared board; buffer built into Sprint 3 | All |
| RK-03 | Integration failures late in Construction | M | H | Walking skeleton in Week 2 forces end-to-end integration before features are built; CI runs on every push | Member B |
| RK-04 | External reputation API rate limits or outage | M | L | Local cache of lookups; hash-chain registry functions independently; demo dataset pre-seeded | Member D |
| RK-05 | Scope creep from stakeholder feedback | M | M | Feedback disposition table: every item formally accepted or declined with reason; baseline change requires supervisor sign-off | Ashraful |
| RK-06 | Live demo failure in presentations | L | M | Recorded backup demo; seeded demo data; rehearsal with timer twice before each presentation | Member C |
| RK-07 | Academic integrity issue from undisclosed tool use | L | H | Standing Log section for tools/AI/code sources with reflection, per unit outline and AHE AI Guidelines | Member D |

# 7. Communication and Governance

- Weekly cadence. One supervisor meeting (minuted in the Log) plus one internal team stand-up. Decisions recorded with justification the same day.

- Change control. Any change to the signed baseline requires a new entry in the refinement register and supervisor acknowledgement — no silent scope changes.

- Disclosure. Every Log entry carries the standing section for tools, libraries, code sources and AI assistance used, with reflection, per the unit outline and AHE Student Generative AI Guidelines.

# 8. Adoption

| Role | Name | Signature / Date |
| --- | --- | --- |
| Supervisor (sighted) |  |  |
| Team representative | Ashraful Islam |  |
| Team member |  |  |
| Team member |  |  |
| Team member |  |  |